## Dashboard
Project name: |  |  | Membership Management Tool (MMT)
Project code: |  |  | MMT
Version of the document: |  |  | 1.0
Brief summary of the scope: |  |  | 0
Signed by: |  |  | <Signer>
Signed date: |  |  | 42022
Signature:
Number of requirements: |  | 23
Requirements by type:
| Functional | 23
| Performance | 0
| Usability | 0
| Interface | 0
| Operational | 0
| States and modes | 0
| Environmental | 0
| Adaptability | 0
| Constraint | 0
Requirements by status:
| New | 23
| Verified | 0
| Approved | 0
| Rejected | 0
| Deferred | 0
| In development | 0
| Completed | 0
| Tested | 0

## Requirements
[9 empty] | Complexity | Status | Types
[9 empty] | Very high | New | Functional
[9 empty] | High | Verified | Performance
[9 empty] | Medium | Approved | Usability
[9 empty] | Low | Rejected | Interface
Project name: |  |  | Membership Management Tool (MMT) | [5 empty] | Very low | Deferred | Operational
Project code: |  |  | MMT | [6 empty] | In development | States and modes
Version of the document: |  |  | 1.0 | [6 empty] | Completed | Environmental
Brief summary of the scope: | [9 empty] | Tested | Adaptability
Constraints: | [10 empty] | Constraint
Assumptions and dependencies: | [10 empty] | Business
Environment: |  |  | Standalone application in Windows platform | [7 empty] | Stakeholder
Participants: |  |  | Haran | [7 empty] | Transition
Prathiba
Signed by: |  |  | <Signer>
Signed date: |  |  | 2015-01-18
Signature:
<Requirement ID> | <Short name of the requirement> | <Type of the requirement> | <Requirement text> | <Components where the requirement is allocated into> | <Ids of the related requirements> | <Current status of the requirement> | <How complex is to technically afford the requirement> | <In case this requirement is not fulfilled, what is the impact to the business needs address by this project>
ID | Title | Type | Description | Allocation | Related requirements | Status | Completixy | Impact in the business
UC_MM_01 | Search members by id / name | Functional | Search member(s) based on Member ID / Member Name | Member Management |  | New
UC_MM_02 | Search members by type | Functional | Search member(s) based on Member Type | Member Management |  | New
UC_MM_03 | View members (with pagination) | Functional | To show the list of members based on the pagination The shown list will contain the pre-defined number of members only | Member Management |  | New
UC_MM_04 | Edit / View member | Functional | To view the details of the selected member from the list of members shown To edit the details of the selected member | Member Management |  | New
UC_MM_05 | Add member | Functional | To add a new member | Member Management |  | New
UC_MM_06 | View payments (with pagination) | Functional | To display the payment history of the selected member | Member Management |  | New
UC_MM_07 | Search payment by date duration | Functional | Search payments of the selected member for the given duration | Member Management |  | New
UC_PM_01 | Search payment by date duration | Functional | Search payments for the given date duration | Payment Management |  | New
UC_PM_02 | Search payment by member id / name | Functional | Search payments by member id / name | Payment Management |  | New
UC_PM_03 | View payments (with pagination) | Functional | To show the list of payments based on the pagination The shown list will contain the pre-defined number of payments only | Payment Management |  | New
UC_PM_04 | Add payment | Functional | To add a new payment | Payment Management |  | New
UC_PM_05 | Edit payment | Functional | To view the details of the selected payment from the payment list To edit the details of the selected payment | Payment Management |  | New
UC_RP_01 | Per member - Member info (PDF) | Functional | To export the profile in PDF for the selected member | Reports |  | New
UC_RP_02 | Per member - Payment Receipt (PDF) | Functional | To export the payment receipt in PDF for the selected member | Reports |  | New
UC_RP_03 | Bulk member export (CSV) | Functional | To export the profiles in PDF for the set of members | Reports |  | New
UC_RP_04 | Payment due for selected duration (CSV) | Functional | To export the payment due records for the selected date duration | Reports |  | New
UC_RP_05 | Payment paid for selected duration (CSV) | Functional | To export the payment paid records for the selected date duration | Reports |  | New
UC_RP_06 | Per member - Meeting letter (PDF) | Functional | To generate general body meeting notification in PDF for the selected member | Reports |  | New
UC_RP_07 | Per member - Payment reminder (PDF) | Functional | To export the payment reminder notification in PDF for the selected member | Reports |  | New
UC_RP_08 | Per member - Payment details (CSV) | Functional | To export payment details in CSV for the selected member | Reports |  | New
UC_DU_01 | Upload member details | Functional | To upload member details into this new tool | Data Upload |  | New
UC_DU_02 | Upload payment details | Functional | To upload payment details into this new tool | Data Upload |  | New
UC_MI_01 | Generate payment due records | Functional | To generate payment due records for active members | Miscellaneous |  | New

## Project_Plan
Module | Usecase Id | Usecase | Task Id | Task | Task Owner | Status | Estimated Effort (in hour) | Start Date | End Date | Time spent (in hour) | Comments
Generic | GEN_01 | Documentation | Task_001 | Guide to Dev Environment setup | Mahendran | Completed |  | 2016-02-18 | 2016-02-18 | 2
Generic | GEN_01 | Documentation | Task_002 | Requirement Specification | Mahendran | Completed |  | 2016-02-20 | 2016-02-21 | 2
Generic | GEN_01 | Documentation | Task_003 | Design Specification | Suyambu | Open
Generic | GEN_01 | Documentation | Task_004 | Sample GUI Screens (By hand) | Mahendran | In Progress | 4 | 2016-02-29 | 2016-03-04
Generic | GEN_02 | Datamodel | Task_005 | Create Schema, Tables | Mahendran | Completed |  | 2016-02-14 | 2106-02-16 | 4
Generic | GEN_03 | Coding | Task_006 | Develop Entities from DB tables | Mahendran | Completed |  | 2016-02-16 | 2016-02-27 | 4
Generic | GEN_03 | Coding | Task_007 | Basic DAO methods | Mahendran | Completed |  | 2016-02-16 | 2016-02-27 | 8 | Basic CRUD methods for each entity - Member, Address, Payment, Constant
Generic | GEN_03 | Coding | Task_008 | Sample End-to-End flow | Suyambu Mahendran | In Progress | 24 | 2016-02-29
Member Mgmt | UC_MM_01 | Search members by id / name | Task_009 | UI related | Person-1 | Open | 4
Member Mgmt | UC_MM_01 | Search members by id / name | Task_010 | Server-side | Person-1 | Open | 1
Member Mgmt | UC_MM_01 | Search members by id / name | Task_011 | DB related | Mahendran | In Progress | 1
Member Mgmt | UC_MM_02 | Search members by type | Task_012 | UI related | Person-1 | Open | 1
Member Mgmt | UC_MM_02 | Search members by type | Task_013 | Server-side | Person-1 | Open | 0.5
Member Mgmt | UC_MM_02 | Search members by type | Task_014 | DB related | Mahendran | In Progress | 1
Member Mgmt | UC_MM_03 | View members (with pagination) | Task_015 | UI related | Person-1 | Open | 4
Member Mgmt | UC_MM_03 | View members (with pagination) | Task_016 | Server-side | Person-1 | Open | 2
Member Mgmt | UC_MM_03 | View members (with pagination) | Task_017 | DB related | Mahendran | Open | 2
Member Mgmt | UC_MM_04 | Edit / View member | Task_018 | UI related | Person-1 | Open | 16
Member Mgmt | UC_MM_04 | Edit / View member | Task_019 | Server-side | Person-1 | Open | 2
Member Mgmt | UC_MM_04 | Edit / View member | Task_020 | DB related | Mahendran | Open | 2
Member Mgmt | UC_MM_05 | Add member | Task_021 | UI related | Person-1 | Open | 2
Member Mgmt | UC_MM_05 | Add member | Task_022 | Server-side | Person-1 | Open | 1
Member Mgmt | UC_MM_05 | Add member | Task_023 | DB related | Mahendran | Open | 2
Member Mgmt | UC_MM_06 | View payments (with pagination) | Task_024 | UI related | Person-1 | Open | 4
Member Mgmt | UC_MM_06 | View payments (with pagination) | Task_025 | Server-side | Person-1 | Open | 2
Member Mgmt | UC_MM_06 | View payments (with pagination) | Task_026 | DB related | Mahendran | Open | 2
Member Mgmt | UC_MM_07 | Search payment by date duration | Task_027 | UI related | Person-1 | Open | 3
Member Mgmt | UC_MM_07 | Search payment by date duration | Task_028 | Server-side | Person-1 | Open | 1
Member Mgmt | UC_MM_07 | Search payment by date duration | Task_029 | DB related | Mahendran | Open | 2
Payment Mgmt | UC_PM_01 | Search payment by date duration | Task_030 | UI related | Person-1 | Open | 1
Payment Mgmt | UC_PM_01 | Search payment by date duration | Task_031 | Server-side | Person-1 | Open | 0.5
Payment Mgmt | UC_PM_01 | Search payment by date duration | Task_032 | DB related | Mahendran | Open | 0.5
Payment Mgmt | UC_PM_02 | Search payment by member id / name | Task_033 | UI related | Person-1 | Open | 2
Payment Mgmt | UC_PM_02 | Search payment by member id / name | Task_034 | Server-side | Person-1 | Open | 1
Payment Mgmt | UC_PM_02 | Search payment by member id / name | Task_035 | DB related | Mahendran | Open | 1
Payment Mgmt | UC_PM_03 | View payments (with pagination) | Task_036 | UI related | Person-1 | Open | 1
Payment Mgmt | UC_PM_03 | View payments (with pagination) | Task_037 | Server-side | Person-1 | Open | 1
Payment Mgmt | UC_PM_03 | View payments (with pagination) | Task_038 | DB related | Mahendran | Open | 2
Payment Mgmt | UC_PM_04 | Add payment | Task_039 | UI related | Person-1 | Open | 4
Payment Mgmt | UC_PM_04 | Add payment | Task_040 | Server-side | Person-1 | Open | 1
Payment Mgmt | UC_PM_04 | Add payment | Task_041 | DB related | Mahendran | Open | 1
Payment Mgmt | UC_PM_05 | Edit payment | Task_042 | UI related | Person-1 | Open | 2
Payment Mgmt | UC_PM_05 | Edit payment | Task_043 | Server-side | Person-1 | Open | 0.5
Payment Mgmt | UC_PM_05 | Edit payment | Task_044 | DB related | Mahendran | Open | 1
Reports | UC_RP_01 | Per member - Member info (PDF) | Task_045 | UI related | Person-2 | Open | 8
Reports | UC_RP_01 | Per member - Member info (PDF) | Task_046 | Server-side | Person-2 | Open | 2
Reports | UC_RP_01 | Per member - Member info (PDF) | Task_047 | DB related | Mahendran | Open | 2
Reports | UC_RP_02 | Per member - Payment Receipt (PDF) | Task_048 | UI related | Person-2 | Open | 4
Reports | UC_RP_02 | Per member - Payment Receipt (PDF) | Task_049 | Server-side | Person-2 | Open | 2
Reports | UC_RP_02 | Per member - Payment Receipt (PDF) | Task_050 | DB related | Mahendran | Open | 1
Reports | UC_RP_03 | Bulk member export (CSV) | Task_051 | UI related | Person-2 | Open | 3
Reports | UC_RP_03 | Bulk member export (CSV) | Task_052 | Server-side | Person-2 | Open | 2
Reports | UC_RP_03 | Bulk member export (CSV) | Task_053 | DB related | Mahendran | Open | 1
Reports | UC_RP_04 | Payment due for selected duration (CSV) | Task_054 | UI related | Person-2 | Open | 3
Reports | UC_RP_04 | Payment due for selected duration (CSV) | Task_055 | Server-side | Person-2 | Open | 2
Reports | UC_RP_04 | Payment due for selected duration (CSV) | Task_056 | DB related | Mahendran | Open | 1
Reports | UC_RP_05 | Payment paid for selected duration (CSV) | Task_057 | UI related | Person-2 | Open | 2
Reports | UC_RP_05 | Payment paid for selected duration (CSV) | Task_058 | Server-side | Person-2 | Open | 1
Reports | UC_RP_05 | Payment paid for selected duration (CSV) | Task_059 | DB related | Mahendran | Open | 1
Reports | UC_RP_06 | Per member - Meeting letter (PDF) | Task_060 | UI related | Person-2 | Open | 6
Reports | UC_RP_06 | Per member - Meeting letter (PDF) | Task_061 | Server-side | Person-2 | Open | 2
Reports | UC_RP_06 | Per member - Meeting letter (PDF) | Task_062 | DB related | Mahendran | Open | 1
Reports | UC_RP_07 | Per member - Payment reminder (PDF) | Task_063 | UI related | Person-2 | Open | 6
Reports | UC_RP_07 | Per member - Payment reminder (PDF) | Task_064 | Server-side | Person-2 | Open | 2
Reports | UC_RP_07 | Per member - Payment reminder (PDF) | Task_065 | DB related | Mahendran | Open | 1
Reports | UC_RP_08 | Per member - Payment details (CSV) | Task_066 | UI related | Person-2 | Open | 3
Reports | UC_RP_08 | Per member - Payment details (CSV) | Task_067 | Server-side | Person-2 | Open | 2
Reports | UC_RP_08 | Per member - Payment details (CSV) | Task_068 | DB related | Mahendran | Open | 1
Data Upload | UC_DU_01 | Upload member details | Task_069 | UI related | Person-2 | Open | 4
Data Upload | UC_DU_01 | Upload member details | Task_070 | Server-side | Mahendran | Open | 8
Data Upload | UC_DU_01 | Upload member details | Task_071 | DB related | Mahendran | Open | 4
Data Upload | UC_DU_02 | Upload payment details | Task_072 | UI related | Person-2 | Open | 4
Data Upload | UC_DU_02 | Upload payment details | Task_073 | Server-side | Mahendran | Open | 8
Data Upload | UC_DU_02 | Upload payment details | Task_074 | DB related | Mahendran | Open | 4
Miscellaneous | UC_MI_01 | Generate payment due records | Task_075 | UI related | Person-2 | Open | 2
Miscellaneous | UC_MI_01 | Generate payment due records | Task_076 | Server-side | Mahendran | Open | 4
Miscellaneous | UC_MI_01 | Generate payment due records | Task_077 | DB related | Mahendran | Open | 4
[6 empty] | Total | 204

## X
Status
Open
In Progress
Completed
Blocked